## UAT Tracker
Ruby+ UAT Final Review Tracker
Final code-review status. Update the UAT result and owner after testing each item.
Release decision: Not ready for full release |  |  | Total UAT items | 23
Primary blocker: Saved cards missing from direct reservation checkout |  |  | Verified in code | 8
|  |  | UAT required | 12
|  |  | Release blockers | 1
|  |  | External dependencies | 2
ID | UAT point | Area | Final review status | Priority | Next action | Review notes
1 | Meal portion sizes auto-selected | Customer app | Verified in code | Medium | Ready for device UAT | Size is single-select; it replaces the base price. Add-ons are added separately and retained in the order payload.
2 | Wallet booking escrow payment fails | Customer app / Backend | UAT required | Critical | Test end-to-end | Code paths reviewed, but wallet booking payment must be tested through payment, escrow and booking confirmation.
3 | Wallet balance stale after booking | Customer app | Verified in code | High | Ready for device UAT | Home and Pay share wallet cache with refresh and invalidation handling.
4 | Quotations not downloadable | Customer app / Business app | UAT required | High | Test on physical device | Download action exists; confirm it downloads and opens a quotation on iOS and Android.
5 | Saved cards missing for services | Customer app | Release blocker | High | Implement before release | Saved cards work for quotation payment but not direct service or room reservation checkout.
6 | No opt-in to save cards | Customer app | Verified in code | Medium | Ready for device UAT | Save-card option is explicit and off by default where saved-card payment is implemented.
7 | Bookings tab segments oversized | Business app | UAT required | Medium | Test on target devices | Confirm Upcoming, Active, Past and Cancelled segments fit and scroll correctly on small screens.
8 | Platform and service fee errors | Customer app / Backend | UAT required | Critical | Test end-to-end | Only the category platform fee should apply to orders. Verify displayed and charged totals against admin fee settings.
9 | Card payments missing from history | Customer app / Backend | UAT required | Critical | Test end-to-end | Confirm a successful card payment appears once in transaction history with the correct amount and status.
10 | Merchant cannot cancel orders | Business app / Web / Backend | Verified in code | Critical | Ready for device UAT | Merchant cancellation refunds first. A terminal cancellation is not persisted if refund processing fails.
11 | Home and Pay wallet balance mismatch | Customer app | Verified in code | High | Ready for device UAT | Both views read the shared wallet query and receive refresh/invalidation updates.
12 | Applying points at checkout fails | Customer app / Backend | UAT required | High | Test end-to-end | Test a fresh unpaid order with a valid points balance and verify the discount and payment total.
13 | OTP codes land in junk | Email delivery | External dependency | High | Verify domain email setup | Requires production checks for SPF, DKIM, DMARC and sending-provider reputation; cannot be confirmed by application code alone.
14 | Play Store developer verification | Google Play Console | External dependency | High | Complete externally | Google account verification is outside the codebase and must be completed in Play Console.
15 | Subcategories shown as categories | Customer app / Taxonomy | UAT required | Medium | Test taxonomy screens | Verify category and subcategory labels with current production taxonomy data.
16 | Hotels and Shortlets 24/7 hours | Business app / Customer app / Backend | Verified in code | Medium | Ready for device UAT | 24/7 availability is supported during onboarding and settings, and displays correctly to customers.
17 | Slow back-to-home navigation | Customer app | Verified in code | High | Ready for device UAT | Back navigation uses history first and avoids forced routing to Home.
18 | Manual What’s Hot selection | Admin web / Backend | Verified in code | Medium | Deploy and UAT | Admin can add or remove a live business from What’s Hot. City-scoped featured businesses and advertisers remain included.
19 | Long app loading time | Customer app / Backend | UAT required | High | Benchmark on real devices | Caching and deferred home loading are in place. Capture cold-start and home-ready timing on production-like networks.
20 | Ruby+ Select posts link to profile | Customer app / Backend | UAT required | Medium | Test interaction | Open image and video posts and verify linked business posts route to the correct profile.
21 | Optimize Ruby+ Select media | Backend / Customer app | UAT required | High | Benchmark media playback | Transcoding code exists. Verify upload processing, playback startup, buffering, image fallback and mobile data usage.
22 | Sub-branches need no approval | Business app / Backend | UAT required | High | Test branch creation | Create a branch and confirm its approval path matches the agreed business rules without unintended admin gating.
23 | DeoluAI response speed | Backend / Customer app | UAT required | Medium | Benchmark response time | Prompt caching, location reuse, short response limits and latency logging exist. Measure real response latency before sign-off.