DEVELOPMENT PROPOSAL

Lagos Dispatch & Delivery Marketplace

Phase 1 MVP - Product, Engineering and Launch Delivery

| Prepared for Eni / Project Sponsor | Proposal date July 2026 |
| --- | --- |

Executive summary

We propose to design, build and launch a production-ready Phase 1 marketplace for Lagos businesses and independent delivery providers. The MVP will use one mobile application with role switching, supported by an operations-first web admin console and a secure backend designed around verifiable delivery evidence and a ledgered escrow wallet.

Commercial recommendation A fixed MVP investment of ₦6,000,000 delivered over 18 weeks. This proposal prioritises the trust layer - escrow, KYC, proof of handover/delivery, tracking and disputes - before Phase 2 growth features.

MVP outcomes

Businesses can post, fund and monitor delivery jobs with parcel photos, declared value, pickup/drop-off pins, receiver details and suggested pricing.

Providers can complete KYC, browse and batch qualifying jobs, navigate deliveries, capture proof photos and receive wallet payouts.

Operations can review KYC, resolve disputes, monitor live jobs, suspend providers and manually release or refund escrow when required.

Every job produces an auditable trail: ledger entries, GPS points, handover confirmations, receiver OTP and proof photographs.

Delivery approach

The build will use a single mobile codebase (React Native or Flutter, agreed at kickoff), a secure API and PostgreSQL/PostGIS backend, realtime job updates, S3-compatible photo storage and a responsive web operations console. Paystack or Flutterwave, SMS/OTP, KYC and maps will be integrated through their approved APIs.

SCOPE, DELIVERABLES & DELIVERY PLAN

What will be delivered

Included deliverables

| Workstream | Included in MVP |
| --- | --- |
| Mobile marketplace app | Single account with Business/Provider role switch; registration, OTP, job posting, job board, batch acceptance, live tracking, camera proof, ratings and wallet views. |
| Escrow and wallet platform | Double-entry wallet ledger, fee collection, escrow lifecycle, refund/release controls, bank payout requests and transaction history. |
| Provider trust & safety | KYC workflow, document expiry tracking, identity-provider integration, guarantor details, provider rating and suspension controls. |
| Admin operations console | KYC queue, job monitor, dispute evidence console, manual escrow actions, provider/business administration and configurable rules. |
| Realtime & communications | Live status/GPS updates, push notifications, SMS fallback for receiver OTP and operational alerts. |
| Launch readiness | Quality assurance, staging/production setup, security hardening, source-code handover, deployment notes and administrator training. |

18-week delivery timeline

| Period | Milestone | Acceptance output |
| --- | --- | --- |
| Weeks 1-2 | Discovery and product design | User journeys, delivery rules, UX prototypes, data model, integration plan and acceptance criteria. |
| Weeks 3-5 | Platform foundation | Authentication, role switch, profiles, KYC/document flow, wallet ledger, admin foundations and environments. |
| Weeks 6-9 | Core marketplace | Job creation, pricing v1, job board, qualification filters, acceptance, batching and payment collection. |
| Weeks 10-12 | Delivery execution | Pickup/delivery evidence, receiver OTP, GPS tracking, escrow release, payouts and notifications. |
| Weeks 13-15 | Operations & risk | Disputes, admin controls, provider suspension, audit trail, offline resilience and restricted-corridor warnings. |
| Weeks 16-18 | Pilot and launch | End-to-end QA, UAT in two Lagos clusters, performance/security fixes, app release and handover. |

Target launch: two Lagos clusters, supporting a controlled MVP pilot before corridor-by-corridor scale-up. Phase 2 subscriptions, rating-gated tiers, advanced route optimisation, trucks/inter-city and public integrations are intentionally excluded from this Phase 1 estimate.

COMMERCIALS & PAYMENT TERMS

MVP investment and engagement terms

Cost breakdown

| Cost component | Amount (NGN) |
| --- | --- |
| Product discovery, technical architecture & UX | ₦500,000 |
| Mobile application - Business and Provider roles | ₦1,500,000 |
| Backend, realtime services & geo-enabled database | ₦1,800,000 |
| Escrow wallet, payments and payout integrations | ₦800,000 |
| Admin, KYC, disputes and risk controls | ₦600,000 |
| QA, security hardening, release & deployment | ₦450,000 |
| Project management, documentation & handover | ₦350,000 |
| Total fixed Phase 1 MVP investment | ₦6,000,000 |

Payment schedule

| Payment point | Amount | Trigger |
| --- | --- | --- |
| 50% upfront | ₦3,000,000 | Due on signing. Reserves the delivery team and starts discovery, UX and platform foundation. |
| 30% milestone payment | ₦1,800,000 | Due after the working MVP beta demonstrates job posting, provider acceptance/batching, payment escrow and core tracking. |
| 20% launch payment | ₦1,200,000 | Due after UAT acceptance, production deployment and source-code/documentation handover. |

Upfront payment required Kickoff begins upon receipt of the 50% upfront payment (₦3,000,000) and written confirmation of the selected payment provider, KYC provider, maps provider and launch entities.

Commercial assumptions & exclusions

The fixed price covers Phase 1 MVP scope only. Changes that introduce Phase 2/3 features, new delivery regions, additional apps or material workflow changes will be estimated and approved separately.

Third-party operating costs are excluded: payment gateway transaction charges, SMS/OTP, KYC verification, maps/routing, cloud hosting/storage, Apple/Google developer accounts, courier licensing, insurance premiums and legal/compliance fees.

Client supplies brand assets, legal copy, operational fee/cancellation rules, provider verification policy and access to all third-party accounts. UAT feedback is consolidated within five business days per milestone.

Proposal validity: 14 days from issue. Estimated delivery begins after kickoff dependencies are available. The first priority is a safe two-cluster pilot; scaling decisions will be informed by live delivery and pricing data.